## KY Windage
Rough Order of Magnitude
| Total | Year 1 | Year 2 | Year 3 | Year 4 | LOE (hrs) | Annual
Surveys | 285 | 71.25 | 71.25 | 71.25 | 71.25 | 16 | 1140
Router | 240 | 60 | 60 | 60 | 60 | 4 | 240
Switch | 720 | 180 | 180 | 180 | 180 | 4 | 720
UPS | 200 | 50 | 50 | 50 | 50 | 2 | 100
EVM | 200 | 50 | 50 | 50 | 50 | 1 | 50
Users | 24000 | 6000 | 6000 | 6000 | 6000 | 0.25 | 1500
3750

## Weighted Site
Site Size Analysis
| Units @ | Hours of effort to complete the survey |  |  |  |  | Site |  |  | Hours/Year (24 sites per size per year)
| Small | Admin | Survey | Inventory | Printer | Labor | Travel | Total |  | Small | Sites | Equip Hrs | User Hrs
Survey | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 6 |  | 492 | 24 | 10.5 | 4
Router | 1 |  |  |  |  | 4 | 0.5 | 4.5
Switch | 1 |  |  |  |  | 2 | 0.5 | 2.5
UPS | 1 |  |  |  |  | 2 | 0.5 | 2.5
EVM | 1 |  |  |  |  | 0.5 | 0.5 | 1
Users | 16 |  |  |  |  | 0.25 |  | 4
[7 empty] | Hours | 20.5
| Medium | Admin | Survey | Inventory | Printer | Labor | Travel | Total |  | Medium | Sites | Equip Hrs | User Hrs
Survey | 1 | 1 | 3 | 3 | 2 | 9 | 2 | 11 |  | 1002 | 24 | 14.5 | 16.25
Router | 1 |  |  |  |  | 4 | 0.5 | 4.5
Switch | 3 |  |  |  |  | 2 | 0.5 | 6.5
UPS | 1 |  |  |  |  | 2 | 0.5 | 2.5
EVM | 1 |  |  |  |  | 0.5 | 0.5 | 1
Users | 65 |  |  |  |  | 0.25 |  | 16.25
[7 empty] | Hours | 41.75
| Large | Admin | Survey | Inventory | Printer | Labor | Travel | Total |  | Large | Sites | Equip Hrs | User Hrs
Survey | 1 | 2 | 8 | 9 | 3 | 22 | 8 | 30 |  | 2556 | 24 | 31 | 45.5
Router | 1 |  |  |  |  | 4 | 2 | 6
Switch | 8 |  |  |  |  | 2 | 2 | 18
UPS | 1 |  |  |  |  | 2 | 2 | 4
EVM | 1 |  |  |  |  | 1 | 2 | 3
Users | 182 |  |  |  |  | 0.25 |  | 45.5 |  | Total/Yr | Sites | Equip Hrs | User Hrs
[7 empty] | Hours | 106.5 |  | 4050 | 72 | 56 | 65.75
This sections takes the total number of project hours for year 1 and assigns those hours
to the billable equipment by a ratio that considers when users checks are likely to be
required (i.e. I do not anticipate user checks if only a UPS or EVM is replaced)
Installation Hours (all site sizes combined) | [6 empty] | Users allocated to: |  |  | TechRate
| Rtr | Sw | UPS | EVM | Total |  | Rtr | Sw |  | 75
Equip Hrs | 15 | 27 | 9 | 5 | 56 |  | 20% | 80%
Users Hrs | 13.15 | 52.6 |  |  | 65.75 |  |  |  |  | Price
Comb Hrs | 28.15 | 79.6 | 9 | 5 | 121.75 |  |  |  |  | 303750
Percentage of total installation labor hours assigned by equipment
Non-wgt | 26.79% | 48.21% | 16.07% | 8.929% | 100%
Weighted | 23.12% | 65.38% | 7.392% | 4.107% | 100%
Non User-Wighted Cost (Cost of user checks distributed evenly among all equipment)
| Rtr | Sw | UPS | EVM
Total Cost | 81361.6071 | 146450.8929 | 48816.9643 | 27120.5357
Pieces | 60 | 180 | 50 | 50
Item Cost | 1356.0268 | 813.6161 | 976.3393 | 542.4107
User Wighted Cost (Cost of user checks distributed among router and switch only)
| Rtr | Sw | UPS | EVM
Total Cost | 70230.4928 | 198591.3758 | 22453.7988 | 12474.3326
Pieces | 60 | 180 | 50 | 50
Item Cost | 1170.5082 | 1103.2854 | 449.076 | 249.4867 |  |  | Sanity check: |  | 303750
Travel: | Total resouce travel time divided amongst each equipment (.5 = 1 resouce * 2 hrs; 2 = 4 resources * 2 hrs)

## Weighted Equipment
WAN-LAN Installation Analysis
| Project | Regional | Tech | Site
Small | Manager | Lead | Team | Travel | Total
Survey |  | 8 |  | 2 | 10
Pre-Install |  | 8 |  | 2 | 10
Prior to Install |  | 4 |  |  | 4
Week of Install |  | 2 |  |  | 2
Onsite |  | 2 |  | 2 | 4
Post Install |  | 8 |  |  | 8
|  |  |  | Hours | 38
| Project | Regional | Tech
Medium | Manager | Lead | Team | Travel | Total
Survey |  | 8 | 8 | 4 | 20
Pre-Install |  | 8 |  | 2 | 10
Prior to Install |  | 4 |  |  | 4
Week of Install |  | 3 |  |  | 3
Onsite |  | 6 |  | 2 | 8
Post Install |  | 8 | 16 | 4 | 28
|  |  |  | Hours | 73
| Project | Regional | Tech
Large | Manager | Lead | Team | Travel | Total
Survey |  | 8 | 32 | 10 | 50
Pre-Install |  | 8 |  | 2 | 10
Prior to Install |  | 4 |  |  | 4
Week of Install |  | 4 |  |  | 4
Onsite |  | 8 | 8 | 4 | 20
Post Install |  | 8 | 40 | 8 | 56
|  |  |  | Hours | 144
| Rate | 75 | Total Sites | 282
Note (1) | Router Upgrade | Cost | # of sites
| Small | 2850 | 113 | 322050
| Medium | 5175 | 99 | 512325
| Large | 9600 | 70 | 672000
|  |  | Total Routers | 1506375
|  |  | Average Router Cost | 5341.7553 | Note (2)
| Switch Upgrade | Cost | # of sites
| Small | 2850 | 113 | 322050
| Medium | 5475 | 99 | 542025
| Large | 10800 | 70 | 756000
|  |  | Total switches cost | 1620075
|  |  | Total number of switches based upon averages | 970 | Note (3)
|  |  | Average Switch Cost | 1670.1804
| UPS |  | Flat Rate | 300
| EVM |  | Flat Rate | 300
Project Costs
| Device | Actual Quantity | Cost
| Routers | 240 | 1282021.2766
| Switches | 720 | 1202529.8969
| UPS | 200 | 60000
| EVM | 200 | 60000
|  | Total Project Value | 2604551.1735
Note (1) | The effort by site table is based on the number of switches installed at the site.
The router upgrade section reduces the installation time by a small number of hours
at medium and large sites to compensate for the installation of one router vice
three or eight switches.
Note (2) | The total router cost is based upon the number of sites cited (282) vice the number of
routers cited in the RFP (240) to arrive at an accurate average cost. This was adjusted
in the project costs section to reflect the actual number of devices in the project.
Note (3) | The total switch cost is based upon the number of sites times the average number of switches
at each site (970) vice the number of switches cited in the RFP (720) to arrive at an accurate
average cost. This was adjusted in the project costs section to reflect the actual number of
devices in the project.